| STEPS TO BRING BACK AS MANY SECTIONS FTF AS POSSIBLE | START DATE |
| --- | --- |
| RO… |  |
| - Update GA classroom capacities in Banner to no social distancing | Thurs 4/29 |
| Colleges/Departments… |  |
| - College Spreadsheets RO will distribute 1 spreadsheet per college, with each department on a separate tab. Requesting 1 complete response per college emailed to roomscheduling@colostate.edu. Three columns to complete per course section offered: - “Do not return to FTF” column to check for any distance or hybrid section. Scenarios may include: - Course is always offered RI online - Dept anticipates accommodation for instructor - A hybrid section that will remain hybrid - Other? - Request increased enrollment caps (up to current room cap) - Notes: Include requests to add or cancel a section. Designate hybrid pairs that should now meet together all FTF. *Please do not request to change days or times or move classrooms. DEADLINE: Friday, May 14 | Mon 5/3 |
| RO…round 1 |  |
| - Hybrid (synchronous) analysis - Move back to FTF if fits in classroom (unless marked “Do not return to FTF” on spreadsheet) - Increase capacities on hybrid sections, per updated classroom caps - Inquiries to depts about more complex hybrid scenarios as needed | Upon receipt of completed spreadsheets from colleges |
| - Increase caps for Hybrid/FTF sections - Includes lectures, labs, recitations - Will fire off WL notifications for continuing students | Upon receipt of completed spreadsheets from colleges |
| RO…round 2 |  |
| - Bring synchronous online sections back to FTF - Only those that are not checked “Do not return to FTF” on spreadsheet - Find rooms - Will require shifting other sections to best utilize larger classrooms - Focus on 100-level first for Ram Orientation | Must start by: Fri 5/28 |
| - Work with depts to review class schedule and make additional suggestions - Request revised section caps (some sections will have moved to different classrooms) | After steps 3-5 are complete, approx. Thurs 7/1 |
| Not yet addressed… |  |
| - Asynchronous hybrid sections - Cannot assign days/times due to scheduling conflicts for already registered students |  |
| - Asynchronous online sections - Cannot assign days/times due to scheduling conflicts for already registered students - Can create additional FTF sections of same course in any available time block |  |