Tuesday Feb. 16 – TCRT

Phase III

RO and Facilities:

- How many sections come back in phase III?

- Any commonalities about types?

- Any new buildings with increased demand?

- Does anything need to be done operationally (supplies, etc.)?

Do students need more places to participate in online courses comfortably?

Pam - Gwen – send the list of study spaces could be sent to students again.

Kristi – can we update the study spaces document with a list of building hours?

Discussion on Fall 2021

Our challenge is bringing increased presence to campus with reduced capacity and then to scale up when we have the ability.

Create a robust on-campus presence to recruit new students and to retain existing students.

- offer new students the opportunity for at least one if not multiple in-person courses.

- support to ensure an equitable lift among the various colleges.

Bring increased presence to campus with reduced capacity and then to scale up when we have the ability.

​Timeline:

February 15: Internal date for RO to process all the initial Fall 21 requests from departments.

February 19: RO finalizes requests, reports on classroom availability

February 26: TCRT - what additional changes should be made (more hybrid or F2F courses)?

D and Julia – How many additional small sections seminars are needed and when can 	they fit? Already have Key, Honors, College Level, Learning Communities, IU 172

RO reopens the CPI to collect changes from departments.

March 1 - Kelly - Syllabus for First Year Seminar in CIM lineup

(March 12: Original date that schedule for Fall 2021 schedule available to students)

Gaye and Steve – what communication is needed to Advising Community – when?

April TBD: Fall 2021 schedule available to students.

Mid-April: Registration begins after Spring Break

Pam – and team - Communication: consider the timeline for messages to faculty, advisory, continuing students, and prospective students.

Deans and Mary - HR Issues: We need to consider TWA and language about vaccines.

Budget: Work with Fall 2020 instructional base – perhaps less on IT.

Provost Pedersen, President McConnell and Lynn Johnson on budget concerns.

RO – D- Julia

- limited capacity for classrooms and section size.

- break large enrollment courses into hybrid considering budget implications?

- How do we afford section breakouts?

- Did we max out our fall capacity in terms of individual sections?

- What classroom availability do we have?

Provost and Deans - discussion with HR, Jeanine Mohr and OGC

What about hiring contracts? What about the employment factor?

Vaccinations for faculty?

If we can’t mandate the vaccine what requirements as conditions of employment and teaching in the classroom?

Create a contract with faculty and determine the language.

Kelly and AUCC First Year Team - First-Year Seminars

- targeted to new students.

- 500 to 700 students not served through a first-year seminar?

- recitations with a capacity of 15 students.

- could engage our entire community in the conversation

not the recitations.

inter-disciplinary scholars – focus on student emotional needs, resilience, 	human  development guidance in the first sessions.

Residence Life – curricular alignment

CO 130-150 – reflective writing connections

first-year seminars in colleges with large enrollments – break down sections

consider the budget impact on the first-year seminars.

Who will teach the first-year seminar break out recitations?

Peer mentor involvement?