Fall scenario planning

The PPT will be asking us to move ahead with three foot distancing in the classroom spaces where it makes sense. Tomorrow we’ll work with the team to discuss deadlines, potentials, etc.

Our team needs to develop a staged approach to increasing the enrollment capacity in many of our scheduled on campus classes.

We need to create a timeline for our tasks and decision making points. Please consider impact and needs of the following considerations from the perspective of your role and units you oversee.

Work with Pam in Provost Communications on all external to campus communication.

- What is possible?

- What should not be possible?

Big Picture Task List

- Establish three deadlines/phases and a stop date

- Determine the most important classes to work on first

  - Evaluate demand and backlogged enrollment courses

- Start looking at all classroom capacities

  - Evaluate special needs of laboratory, performance and maker spaces

- Classroom redesign – arranging physical space

  - Any pedagogical changes needed?

- Seating chart redesign

Phases of return to larger capacity presence on campus:

Provost Communication will liaise with PPT and others on communication

When is it needs, to whom intended?

Deadlines for our three stages:

Phase One: What do we need to know by April 5th if possible?

Phase Two: What decisions should be made by June 1 (start of Orientation)?

Phase Three: What decisions need to be in place and what deadline for a final phase?

Detailed work

How long and to what level will we increase enrollments per section?

Which classrooms are viable?

Which courses are most important to work with?

RO and Deans: What are the criteria for determining which courses would be considered for an increase in capacity and implementation of three-foot distancing?

Who garners the list (classes and rooms) and when would we need that list?

Who/what do we communicate with chairs and faculty about regarding increasing 	enrollment in a 	course?

Classroom Space analysis

Facilities: assess rooms and determine which are viable for three foot distances

Facilities, RO (IS) and Campus IT – which seating charts would need to be updated?

Timeline and staffing needs.

Ask PPT: Will we continue to provision classrooms with hygiene supplies for student and faculty use?

RO and Deans/Associate Deans - Impact Analysis

RO: How many extra seats would we gain by class and overall?

Deans/Associate Deans:  is there a demand and/or waitlist historically?

All: What is the date by which we will not add more people after registration begins

Special space needs courses sub-committees

Jan - laboratory spaces sub-committee

Mark Stetter, David McClean, John Hayes, Mica Glanz from bio (?)

Labs would need to submit request to Marc and PPT to reduce the distancing

Permissions structure

Ben and Lise - maker spaces, performing spaces