Undergraduate Teaching Continuity and Recovery

Meeting on August 5 @ 3:00PM

The Team was joined by Brandon Bernier, Jamie McCue, Gwen Gorzelsky, and Chris LaBelle for an update on Technology, Equipment, and Faculty Preparation.

Update on Technology/Equipment - Discussion on IT technology and equipment. Discussion on supply chain issues and alternative options. Jamie McCue provided on the microphone connectors. She noted there 60 GA classrooms and an unknown number of Departmental classrooms that require a lapel microphone and connectors.

There is an issue of safety in terms of sharing the lapel microphone. One option is purchasing disposable wind screens, which is not ideal. ). Another option is to purchase individual lapel microphones for the instructors.

Information has been passed to Linda Meserve in Purchasing to purchase 600 to 650 microphone connectors. There are significant supply chain issues though. IT is waiting to hear further information from Linda Meserve for locating a vendor to supply microphone connectors by start of term.

Update on Technology/Faculty Preparation - Kelly Long noted a need for a conversation on the intersection between technology and faculty preparation. The Associate Deans had noted a need for increased faculty engagement.

What about lecture capture in classrooms? What faculty engagement opportunities can be made available for training purposes?

Brandon Bernier noted that there was an initial phase of lecture capture for classrooms and an additional phase of lecture capture for 25 GA classrooms. Jamie McCue noted that the first 54 GA classrooms and mobile carts have progressed, which have largely avoided the supply chain issues. These 54 GA Classrooms will be online for the first day of classes. Main components will be delivered in time.

With the additional 25 GA classrooms, there are significant supply chain issues as these classrooms were funded much later. These classrooms might not available for the first day of classes. Julia Murphy noted that she did not use these classrooms in her schedule planning. Information about potential lecture capture capabilities had not been shared with faculty. These classrooms might not be available until after Labor Day.

In addition, there are 60 Departmental classrooms that would have lecture capture added. These Departmental rooms are experiencing the same supply chain issues and delays are expected. Lecture capture capacity has tripled.

What about training for faculty on lecture capture? There have been five sessions as part of Fall Ramp Up that were well-attended. Recordings of these sessions will be posted on the Echo 360 website. IT will have "Train the Trainer" training sessions for IT staff, TAs, and Help Desk staff to serve as the first line of support for faculty.

IT has been hearing from faculty that they want access classroom to view the technology. IT will offer open houses; however, planning in a pandemic environment has not been addressed. It will probably be difficult to present in a meaningful way due to social distancing requirement. Faculty would have to be limited 5 to 6 faculty, which would not be a good use of staff time with 100s of faculty. It would not be an efficient use of IT staff time, as they are needed in preparing classrooms.

IT is exploring options for open house that would move through PPT approval process, if decide to proceed. Discussion on training a few key faculty from each College to assist their other colleagues. Discussion on offering a virtual open house would not solve the training issue as faculty want access to the equipment. An open house is a less likely option. A high-quality video has been filmed with a review on equipment access to be used for training purposes.

What about Echo 360 training opportunities? There are numerous requests for Echo 360 training. Faculty anxiety will increase; therefore, we we want to communicate with faculty about all training opportunities. Clark and Eddy are the buildings available for training on August 10.

Associate Deans have been informed to reach out to Department Chairs to organize training similar to CLA. Faculty will have to submit Return to Work to arrange faculty training. Faculty will merely be able view the classroom layout and available equipment. It is not an in-depth training opportunity.

Will lecture capture via a personal laptop be an option? Are there any training materials? Faculty have access to universal capture. IT has emphasized universal capture in all training materials.

Can we see about a blanket Return to Work approval for training? This is a lot of work for the individual departments for the Return to Work process. Why should every group request submit a request? Jan Nerger noted that she has been waiting two-week for a request already.

Kelly Long noted that this was part of mechanism to signal to Julia Murphy to schedule the rooms. Room Scheduling has been bombarded with individual faculty requests for classroom access. We need to discuss this issue with the Health Team. We would want the Departments to submit their department training request to the Associate Deans for them to submit through the Return to Work. Ken Quintana noted that these requests could be approved provided the Return to Work request is submitted.

We need to coordinate with Julia Murphy about requests for spaces in Clark and Eddy due to limited availability. Can time slots be reserved for faculty from any College/Department to sign up? This would alleviate 64 departments from trying to schedule.

Who would meet with faculty? By organizing by departments, it was the thought that the department would have a staff member available for training purposes. Guidance is needed. IT has been coordinating with IT staff across campus. IT has worked with CLA IT staff on training in preparation of the CLA training opportunities.

It might be important to survey Department Chairs on training needs. How can we be more efficient? Set times for faculty to sign up as available would be helpful. Further discussion offline is needed. Only issue is who would be available to assist. Training might need to be department-specific. Training might need to be generic for others.

What about hiring students to assist with technology in the classrooms? CHHS has a large contingent of students in their IT pool.

Update from Chris LaBelle and Gwen Gorzelsky - How can we encourage more faculty engagement? Faculty need to be prepared to offer courses online.

TILT is halfway through its training offerings. TILT is offering three of their 3-week course modules on best practices. Second module will conclude on August 16. Third module will conclude after Labor Day. Also available is a 6-hour teaching online course. There one or two sections each week. Faculty continue to engage in opportunities. Of the sections completed already, Best Practices in Teaching has a 76 percent completion rate and Teaching Online has a 70 percent completion rate.

Gwen Gorzelsky can discuss with TILT about expanding opportunities into early Fall. Kelly Long noted a short workshop, rather than a 3-week module, would be more beneficial for faculty. Faculty need short, small segments with information, tips, etc. We could encourage faculty with small workshops. Faculty may be less likely to enroll in a module, which requires a longer time commitment.

Gwen Gorzelsky will work on workshop opportunity. She noted that it might be helpful to email faculty about the collection of DIY resources on the Keep Teaching website. What about encouraging small stipends for college-located faculty to guide their colleagues?

Chris LaBelle noted been his focus has been on a 16-hour course development workshop. There has been positive input with a completion rate of 70 percent. He anticipates 200 additional enrollments during the month of August.

There has been a focus on expanding course build efforts. Currently, trending towards 180 course builds for Spring. He anticipates finishing course build cycle in Fall 2020 with 225 course builds. Typically, there is a support of 50 and 60 course builds per term.

CSU Online hosted a virtual open house on August 5 with 40 attendees. There is anticipation of holding additional open houses in the future. Chris LaBelle noted that he is finalizing several media studios in October to expand ability to develop high-production media assets. This would elevate the quality of online courses. He has encouraged their student success group to start of a student ambassador group.

Discussion on building parity between different groups (IT, TILT, and CSU Online).

Update on Seating Charts - Ben Withers noted that the Team has reached out to Facilities about creating seating charts. Would we want paper charts for faculty to fill out each session? What about an electronic seating chart? An electronic seating chart would be easier to track. A paper chart could be easily lost.

Seating chart at the beginning of the semester with students remaining in the same seat all semester. Do we want to assign seats? Let students "assign" themselves to the same seat. Faculty choice on how assigned? Faculty would need to display seating assignment for students and faculty to remember.

Seating charts need to be relatively available for contact tracing. How can this work? Pandemic Team would need rapid access. What about uploading seating charts to a OneDrive folder? How can we provide security and functionality?