Undergraduate Teaching Continuity and Recovery

Meeting on January 7 @ 10:00AM

Agenda Items for 1/7:

- Update on Spring 2021 Requirements

- Brainstorm on Key Decisions and Deadlines

- Discussion on Inputs for Sub-Committees

Update on Legislative Report - Kelly Long provided an update on the progress of the legislative report. Discussion on needs from the Team in drafting the report.

Update on Budget - Cheyenne Hall provided an update on the Spring 2021 Budget.

​

Update on Spring 2021 Requirements - Kelly Long asked the Deans to provide a list of hybrid sections to be offered as F2F in Phase 2 by January 15. We would want to understand the testing requirements needed for the scale up. We would need to know how students would be on campus each day beginning on January 25. We would need to know the amount of tests required.

Discussion on how the information could be obtained. We would only know enrollment by section rather than actual students. Students could be enrolled in more than one section on a given day. We would estimate the number of students based on Fall 2020 for testing.

Update on Communication - Discussion on communication needs. What do faculty need to know prior to January 15? What communication would be sent from central? What communication would be sent from College/Departments?

- Information on Seating Charts - Who would send? A Faculty Checklist would be modified, which would include the link about the seating chart tool. Seating charts should be created on the first day an instructors meets with students F2F.

- Adequate PPE Supplies - Re-emphasize Department Chairs about where to order supplies for departmental classrooms (PPE and Microphones).

We need to ensure consistency in information. Messaging, for the most part, would be sent to the Deans for distribution. Deans could add additional college-specific information as needed. We would want simple and short messages.

Discussion on contact tracing for classrooms/labs without assigned seating. If there is not a seating chart, then all students should be screened/tested. PPT has discussed this issue to address.

Discussion on group work assignments. Paul Mallette, Travis Maynard, and Anthony Marchese have drafted a communication regarding peer-to-peer group work.

Would offices be open in Spring 2021? Ken Quintana noted that we would start the semester at the 50 percent rule. Employees should work remotely if possible. There would be return to work protocols for Spring 2021.

Update on Professional Development - Gwen Gorzelsky has added additional sections of professional development for faculty due to the increased need. She noted that 75 participants have each registered for two sections on Best Practices in Hybrid and Online Courses: Intro and Critical Thinking. An additional section of Creating Assignments has been added with 50 participants.