Undergraduate Teaching Continuity and Recovery

Weekly Summary

2 April 2021

Discussion on Fall 2021 Scenario Planning - CSU has been asked to consider the possibility of moving forward with 3-foot physical distancing in Fall 2021. Starting questions would be the following:

- What is possible?

- What is not possible?

- What is the motivation?

- What are the phases/deadlines?

- What information needs to be gathered?

- What are the next steps? What are the priorities?

Big Picture Task List

- Establish deadlines/phases and a stop date

- Determine the most important classes to work on first

- Evaluate demand and backlogged enrollment courses

- Start looking at all classroom capacities

- Evaluate special needs of laboratory, performance and maker spaces

- Classroom redesign – arranging physical space

- Any pedagogical changes needed?

- Seating chart redesign

What are our up-front assumptions?

- We would not move classrooms out of existing classrooms.

- We might be able to close a section; however, we need to consider the ramifications.

- We would not move large online courses onto campus.

- One real challenge would be hybrid courses. What sections could be fully F2F?

- We would not affect employment. We are not collapsing F2F sections. However, it would largely be a local decision depending upon the individual needs of colleges and departments

- We would not be changing dates and times even if time slots open up in classrooms. We could handle on a limited basis moving certain sections at the local level.

- We could not have sections changing times as RO could not facilitate a large-scale move.

- We need to be aware that some students would still seek entirely remote instruction.

- We would lean towards wearing face masks and receiving vaccinations.

- We would need to gather the room capacities first.

- We need to address the physical nature of the classrooms.

- We need to understand the priorities from college and departments.

- We could return to zero physical distancing for in-person courses.

We would have the following constraints moving forward:

- We would not close sections due to employment demands.

- We would not ask the RO to move sections on a large-scale basis.

What is the timeline?

- Step 1: Identify new capacities for classrooms with RO working on GA classrooms first.

- Step 2: Go/No Go. Do we have the "go" to move forward? If yes, then we move forward with increasing capacities.

- Step 3: Reach out to departments and department schedulers followed by one-on-one emails about increasing individual capacity.

- Step 4: Monitoring waitlists to determine if special attention needed.

- Step 5: Address small sections in large classrooms.

Discussion on classrooms and courses. We would need to information about room capacity first. We want to increase capacity with specific courses. In addition, we would want to retain small section courses for building community with students.

- Online courses would not return to campus.

- F2F courses would have capacity increased where indicated (waitlist courses, backlog courses, etc.) based on department needs.

- Hybrid courses would be the focus due to faculty preferences and student attendance.

- Sections would only be collapsed, where needed and based on department needs.

D Tobiassen Baitinger noted the following:

- We need the new classroom room capacities.

- We need to notify departments about monitoring waitlists and identifying priority courses once registration begins.

- We need to instruct departments about the need to contact Julia Murphy, if increased capacities are approved.

- We need to consider changes to hybrid courses and impact on students with changes made as soon as possible.

Julia Murphy (via chat) provided ideas for adjustments to hybrid sections.

- Departments could increase enrollments in both sections up to the new room capacity.

- Departments could change the instructional format to F2F and add the location to all sections provided the combined enrollment fits into the 3-foot physical distancing capacity and the online portion of the section is synchronous.

- Departments could change the instructional format to F2F and request that the sections be collapsed into one section provided the combined enrollment fits into the 3-foot physical distancing capacity and the online portion of the section is synchronous.

Ben Withers (via chat) noted the need to message the following:

- Ken Quintana would be working on capacities for labs and studios.

- We need to inform instructors not to contact RO about individual section changes. Instructors need to work directly through department schedulers.

- We need to emphasize that changing course times would not be made once students register.

- Departments could review adjustments to classroom capacities, based on 3-foot distancing, which would need to be verified.

- We could add new sections to be scheduled in currently open classrooms.

Ben Withers (via chat) noted two things:

- We need to calm individual faculty so they would not "bother" the RO.

- We need talk with the Associate Deans.