Undergraduate Teaching Continuity and Recovery

Agenda

5 April 2021

Assumptions:

- Large lecture courses (99+) will remain remote.

- The current Schedule of Courses stands:

  - We will keep current class/section times. We will not move a 4:00PM section to 9:00AM based on instructor preference.

  - We will keep sections in current classrooms

  - We will keep the number of sections. We will avoid closing a section to increase enrollments in another section unless enrollments are below a minimum standard.

  - We will consider ramifications for CCA faculty in decisions to eliminate sections.

  - We will adjust hidden sections, which have no enrollment.

- We will add new sections to be scheduled in currently open classrooms.

Timeline:

Step 1: Immediate: Identify new capacities for classrooms with RO working on GA classrooms first.

- Kristi Buffington and her team will assess GA classrooms and establish 3-foot physical distancing capacities.

- Ken Quintana will work on capacities for labs and studios.

- Departments can assess their departmentally-controlled classroom spaces while working with Ken Quintana for approval.

- RO will assess which hybrid courses can be fully F2F according to classroom size.

- Departments will monitor waitlists and identify priority courses once registration begins.

Step 2: Go/No Go. Timeframe will be dependent on Larimer County and PPT.

- Provost will provide the "go" to move forward? If yes, we will move forward with increasing capacities.

- TCRT will reach out to departments and department schedulers, which will be followed by one-on-one emails about increasing individual capacity.

Step 3: Summer

- Departments monitor waitlists to determine if special attention needed.

- RO will address small sections in large classrooms and change if possible.

- Department Schedulers work with Julia Murphy if increased capacities are approved.

We will need to further consider ASAP how adjustments to hybrid sections will function. This should include the following:

- Can some decisions about hybrid courses be made at an early date (during upper-class registration, prior to new student) with students informed as soon as possible?

- Can Departments increase enrollments in sections up to the new room capacity?

- Can Departments change the instructional format to F2F and request that the sections be collapsed into one section provided the combined enrollment fits into the 3-foot physical distancing capacity and the online portion of the section is synchronous?

Action Items and Messaging:

An overview of the information above should be shared ASAP with the Deans and the appropriate Associate Deans of all 8 colleges. This message should stress:

- We will inform instructors not to contact RO about individual section changes. Instructors need to work directly through department schedulers.

- Associate Deans can help identify F2F and lab/studio sections where increased capacities will promote academic performance.

- We will not change course times once students register.

- Departments can begin to assess 3-foot physical distancing in departmentally-controlled rooms.