Teaching and Learning Continuity Fall 2021 Outline

Possible (internal) Benchmark Goals for Fall Instruction: Setting even a provisional goal helps us understand what strategies we should follow (there are relationships that connect these goals as well, so achieving one may help achieve others).

- Have hybrid/F2F sections equal or greater than 75-80%. (Fall 2020=64%)

- Aim for a higher percentage of 1st year students who have 2,3 (or 4) or more classes that are hybrid/F2F. In Fall 2020, 51% of students had 3 or more in-person sections and another 20% had two or more.  Can we aim for 70-80% in 3 or more?

- Base goals on overall, headcount enrollment. In Fall 2020 by headcount, 55% of enrollment was in remote instruction; do we want to get to 55% in person for Fall 2021?

Timeline for Fall 2021 course scheduling and registration:

| Feb 12 | RO done w 1st round of edits |
| --- | --- |
| Feb 15 | Present data to Teaching Continuity & Recovery Team |
| Feb 17 | TCRT to communicate next request for changes to academic depts |
| Feb 19 – Feb 26 | CPI open to collect changes from depts. (1 wk.) |
| Mar 1 – Apr 2 | RO process changes submitted through CPI (5 wks.) |
| Apr 2 | Open Plan Ahead to students |
| Apr 5 | Registration opens for FA21 |
| Ongoing… | Continue to add AUCC sections during 4-8pm for 1st yr. students (June reg.) |

Yellow: Crucial decision points for TLCR to identify how to increase in-person learning. Here are some tactics to consider re: increasing in-person instruction compared to Fall 2020.

- Increase course capacities in hybrid and traditional F2F. Will require PPT approval to reduce social distancing rules. (not likely)

- Create new sections in available classrooms (will be in unpopular timeslots like 8 am). This needs to align with request to colleges to add sections in targeted strategic areas: First Year and Seniors.

- First-year seminars/fire-side chats (will be limited to 15 person enrollments, so will need many sections.)

- Be prepared to bring back current hybrid to traditional (will not actually increase in-person enrollment since these sections are already counted; does increase F2F contact time and F2F%.  This decision is dependent on relaxed social distancing; it is relatively easy to implement).

- Bring selected online large enrollment lectures back to campus (dependent of rooms, faculty availability)

  - Bring them as hybrid. Dependent on room availability.

  - Split into smaller, independent sections (RO will share data on available classrooms on Monday, showing available classrooms per time slot. Sections will need to be very small (15 students) unless they are at 8am or after 4pm and rooms then are limited.)

- Increase capacities of already scheduled hybrid/F2F (move some to larger rooms; schedule in new spaces like UCA? Also, if physical distancing expectations change)

- Focus on required major courses in some departments/colleges (not just AUCC). This means identify and target units that in Fall 2020 had low in-person rates in their majors; might be able to bring more department controlled rooms in to the mix?).

Areas where we need to do work:

Determine strategies to increase in person learning opportunities (by mid-February)

Communication: timeline for messages to each based on our work (not campus-wide communications):

Deans/Chairs: message from TLCR about the desire to increase in-person learning from Fall 2020; requests for whatever specific help (new sections, split large lecture, 1Y seminars) we need in February to complete the Fall schedule.

Faculty/staff: now, through deans and chairs regarding Fall in-person goals, new section/section change needs. Later, from Central/Provost: note about in-person goals, that more information from HR about fall accommodations, etc. will be forthcoming, etc.

Advisors: after Fall schedule is complete, describe campus goals for in-person, etc. Steve Dandaneau will assist.

Students: later in spring, before advising and registration. (created by Student Communication sub-group.)

Messaging to prospective students. The Provost indicated last week that our academic plans should drive the messaging to this group, rather than have us react to what is developed by other campus units (Recruiters, Admissions, Central Comm). We discussed taking this basic message: There are tons of options for in-person learning here at CSU; there are other high-quality options, too. We will meet your needs.

Resolve issues through HR: TWA, language about vaccines. At least two deans to reach out to HR to clarify when and how of TWA; begin to develop policies and communication about HR-issues around vaccines, mandates as a condition of employment and TA appointment, and the classroom environment.

Determine Budget Parameters: We will proceed with Fall 2021 schedule creation with the understanding that because we are building on the Fall 2020 schedule, we will need to budget for at least the same number of sections; new in-person options and summer enrollment patterns (among other things) will determine changes to the Fall 2020 base. Other budgetary issues (student assistants, faculty development and training, equipment) will be determined via Kelly Long at a later date.