TEACHING CONTINUITY AND RECOVERY TASK FORCE:

UNDERGRADAUTE SUBCOMMITTEE

Kelly Long, Chair; Steve Dandaneau, Jan Nerger, Ben Withers, Lise Youngblade

This subcommittee was charged with planning fall undergraduate instruction under three scenarios: 1) open campus on time with social distancing protocols, 2) delayed start to the semester with restrictions and contingencies, 3) all online. In accordance with President McConnell’s statement that “we fully intend to be back on campus and operational for the fall semester,” our deliberations focused on the open campus scenario. This report begins with an implementation recommendation and urgently needed actions followed by evaluation of the models in our charge. We conclude with budgetary considerations and brief addenda.

Implementation Recommendation

To effectively plan for any fall semester scenario, it is critical that CSU establish, empower, and fund a Teaching & Learning Implementation Task Force (crucially, by no later than May 15).

The Task Force would work with the Provost to make key academic decisions and allocate resources necessary for a successful Fall Semester 2020. Five subcommittees are proposed:

- Space and Scheduling Subcommittee: Work with the Office of the Registrar and colleges to identify appropriate instructional spaces.

- Faculty Development: Prepare training and workshops consistent across all colleges in collaboration with the Online Implementation team.

- Classroom Hygiene and Safety: Work with Facilities and Office of the Registrar to establish protocols based on state and campus recommendations, ensure supplies are available and adequate, prepare guidelines for faculty and staff, stand ready to adjust protocols as needed.

- First Year Success: consider needs of incoming students, identify approaches to scheduling that maximizes engagement and academic success, collaborate w/Student Success and advising personnel.

- Graduate School/GTA Coordination.

Summary of Urgent Actions Needed/Underway

- Expand Fall Semester Instructional Time by 4 Hours M-F and by 8 Hours on Saturdays. This change must be communicated by May 15 so that fall offerings and new student registration can include courses/sections with 4:00-8:00 p.m. M-F starts and Saturday meeting times.

- Change registration for Transfer Students from May 11 to May 28. Transfer student fall semester registration was changed to a synchronous model and will be available on May 28th.

- Advise Instructional Staff on Fall Semester Instructional Formats.  The provost has prepared a fac/staff communication for May 10. This message may need to be repeated and reinforced.

- Establish Fall Semester Decision Timeline. If, for example, health-&-safety protocols require that F2F gatherings cannot exceed 50, then we recommend fully online fall course work.

- Implementation Committee Members. To facilitate efficiency and efficacy, we suggest an implementation committee be formed immediately. Members from the Teaching Continuity committee Long (chair), Dandaneau, Nerger, Withers, & Youngblade could form the basis of the committee with additional subcommittee experts added as needed.

EVALUATION OF THE THREE MODELS

- Open Campus on time with social distancing protocols

Our goal in this scenario is to maximize F2F instruction, the sine qua non of residential university experience. This model is most effectively implemented, assuming conducive health-&-safety conditions, by expanding instructional time, using non-academic spaces for instruction, encouraging hyflex and hybrid course formats, and moving many large enrollment section courses online.

Based on analysis of classroom square footage and assuming 6’ distancing, we estimate that no more than 30-40 percent of classroom seats can be utilized at any given time. However, if the above tactics and others are pursued effectively, we believe CSU could offer perhaps twice as much F2F instruction as this static estimate suggests. The campus can achieve this goal only if immediate steps are taken to authorize decisions enabling campus priorities and preparations.

Priorities and Principal Considerations

- Fundamental priority: maximize F2F instruction for currently enrolled and new students.

- Health and safety considerations are paramount.

- F2F is limited by reduced classroom density, e.g. 6’ distancing, maximum gatherings based on state/county mandates in Fall (>50, >100).

- Priorities for distribution of F2F instructional opportunities:

- Courses requiring specialized facilities (e.g. art studios, science labs, etc.)

- Courses for freshman (e.g., large AUCC lectures online w/F2F breakout sessions).

- Courses prioritized by departments (e.g., based on pedagogy, graduation requirements).

- To maximize F2F offerings:

- extend M-F instructional time by 4 hours per day (budget implication: CSU will need to add security for the safety of evening students and for extended facilities operations).

- add 8 hours of instructional time on Saturdays (budget implication: same as above).

- schedule classes in non-classroom facilities including in LSC meeting rooms and LSC Grand Ballroom, 8:00 a.m. to 5:00 p.m., for large-enrollment class meetings (possible maximum capacity at one-third of non-COVID max. capacity or 500). Possibilities may also be available in Canvas Stadium, Moby Arena, UCA, South Gym, Drake Center, and the Lincoln Center (budget implication: rent, transportation, security, etc.). Note: if gathering size limits remain in place, then it would not be sensible to secure large venues.

Additional Requirements

- Cleaning supplies readily available in or near all classrooms.

- Appropriate cleaning enforced (e.g., students clean their own spaces before exiting room).

- Necessary PPE for faculty, staff, students available—including face masks.

- Physical space modifications (e.g. plexiglass to divide lab benches, doubling occupancy).

- Additional campus security for extended evening and weekend instructional hours.

- Students and faculty are symptom-free. Requires repeated screening. Need screening forms, temple thermometers (at a minimum; serology at a maximum); increased health staffing, etc.

To the degree these assumptions and requirements cannot be met, fewer courses can be offered F2F and therefore will need to move to online formats. Preparing ASAP for online formats is therefore critical. This move will also facilitate online instructional quality.

Additional Considerations

- We anticipate that a significant percentage of the university community will not, due to health concerns, be able to engage in F2F instructional formats. Others will not wish to. In themselves, these considerations underscore the need for readily available online options.

- More courses will require lectures via remote format.  This will require lecture-capture (with open captioning) equipment be added into a number of classrooms. Synchronous offerings should be encouraged with provisions made for lecture capture/recording so students can engage them asynchronously (budget implication: equipment/installation costs).

Classroom Hygiene and Protocols

- Hygienic protocols require time and therefore impact Course Schedules – 3 options

  - Reduce class period by 10 min. to provide 20 min. for cleaning between classes. Add online components to compensate for lost instructional time and to avoid any effect on accreditation. Faculty adjust content/expectations accordingly.  Recommended

  - Schedule GA classrooms for every other time period and clean during the intervening hour. This would, however, reduce RI teaching capacity by 50%. Not recommended.

  - Adjust the uniform time code to include at least 30 minutes cleaning time between classes. This would reduce instruction time per classroom per day AND the Office of the Registrar would have to manually adjust 5,310 sections.  Not recommended.

  - Hygienic protocols within classroom spaces. Options/considerations include:

- Students clean their own spaces before/after classes – may have legal ramifications, however, especially if number of virus cases increases.  Recommended

- Facilities staff – currently not enough staff in Facilities to clean rooms.

- Cleaning supplies need to be in every room/hallways and maintained.

- Protocols for entering and leaving spaces need to be developed

Course Scheduling

In order to maximize the number of F2F experiences offered to the most students, classes should generally remain in the same room in which they are typically scheduled. This will require most courses to divide the students into multiple smaller groups in order to maintain 6’ distance requirement. Decisions would generally be left to the instructor, but their options include hybrid: remote lecture + students divided into 2 or 3 groups for F2F class meetings during select class periods; and hyflex: providing online and F2F options for students rather than a rotation.

- Approaches for Large Lecture Courses (100+ capacity). The fall course schedule includes approximately 240 sections of courses over 100 students. Since we are assuming no more than 50 people can be in the same space at the same time, all large courses will need to either be fully online or divide into lower enrollment sections. We have developed more than six options that departments will use to address this shift.

- Mid-Capacity Courses (25-99) The fall course schedule currently includes 420 sections with between 45-80 students. These courses will need to relocate to larger classroom spaces or form smaller units via online lectures and/or combinations of F2F breakouts (per above).

- Low Enrollment (≤ 24) Courses. The fall course schedule includes some 1,900 sections with fewer than 24 students (e.g. studios, labs, and practicum). They will need to adapt to distancing as well, but our hope is that they will be able to accomplish this with relatively minimal disruption. Many of these spaces are departmentally controlled.

Expanded Academic Instructional Time

- If we assume an 8am – 9pm (class end time) schedule, there are 27 timeslots x 16 GA classrooms that can seat more than 50 students following social distancing guidelines (information provided by CSU Facilities). This results in 432 available scheduling slots. We propose to add to these with Saturday instructional time as well.

- First-year students begin registration June 8. If we act quickly, we have time to offer many freshman student-focused courses in the 4-8pm period, which we think will increase their F2F instruction and serve them in other ways as well. This will require shifting some existing AUCC courses and/or developing additional sections of courses. Large section lecture courses can also offer breakout sections during extended M-F evening hours.

- Market the concept that cohesion among first-year students will be cultivated and reinforced by course groupings in the late afternoon and early evenings. Limit opportunities for residence hall occupants to gather unsafely during culturally normative “recreational time.”

- Add credit-bearing small group community-building seminars that address mental health, diversity, and other vital community issues.

- Encourage graduate courses to move into the 8:00 a.m. periods, after 4 p.m., and Saturdays.

How much F2F is possible?

In the proposed model, if EVERY course is retained in its regularly assigned time and place, then, theoretically, 100 percent of courses could have F2F components. With distancing, every student could experience F2F 33-50 percent of the time in each course, while the remaining 50-67 percent would be offered online. Many additional variables are, however, in play.

- 240 sections of courses over 100 students

- 420 sections between 45-80 students.

- 1900 small enrollment (≤ 24) courses.

What could increase the F2F percentage?

- State or County decreases social distancing beyond 6 feet

- State or County increases maximum gathering size to more than 50

- Large lecture classrooms vacated by large courses allow medium-sized courses to use locations. This would permit some courses to be offered 100% F2F for all students.

- Use of 27 additional hours of scheduling time by adding 4 hours to the M-F schedules and offering classes on Saturday (as proposed).

- Use of alternative non-classrooms, e.g. LSC, Moby, UCA, Alumni Center, Canvas, etc.

- Faculty who opt to teach online free classroom space for other courses to be offered F2F.

- Departments enthusiastic for 8-week courses offer them in the second half of the Fall.

What could decrease the F2F percentage?

- State or County increases in social distancing beyond 6 feet

- State or County regulates maximum gathering size under 50

- State or County returns to Stay-at-Home Policy

Immediate General Steps for Departments, Colleges, and Campus

- Increase lecture capture capacity (only 52/184 classrooms are currently enabled)

- Determine actual enrollments. Departments “true up” estimated course enrollment-capacity with actual enrollment trends

- Department-specific lists of “priority” courses: Preliminary lists created.

- Departments have identified courses/instructors who prefer to teach remotely in the fall: Preliminary numbers identified.

- Develop college-driven list of large-lecture courses and options for offering as hybrid. Process started.

Registration: Keep on schedule to send positive signal to incoming students.

- For new full-time, first-time freshman, begin registration on June 8, with first orientation.

- For new transfer students, shift access to the asynchronous orientation until May 26 and delay their registration to May 28-29.

Scenario 2:  Incomplete Face-to-Face Fall Semester

In this scenario, we assume that Fall Semester is: 1) delayed from opening or 2) begins on campus but must pivot to remote learning during the semester (akin to SP 2020).

Version 1): Fall semester is delayed:

- This assumes no on-campus experience is available for some amount of time at the beginning of the semester.

- One option is to fully delay the start of courses to the day campus opens.

  - This creates challenges with contact time. A one-week delay might be accommodated, four-week more difficult, and an 8-week version of courses would complicate room use.

  - While we are too late to implement a wide scale 8-week version, if we must pivot students would complete a maximum of half of their course-work on campus (perhaps the other half completely online).

  - Disadvantages include students needing to drop courses as a result of increased demands of intensive courses. Students might be more likely to delay until spring semester.

- Another option utilizes a fully a hybrid model that starts the 16-week semester remotely with full online-delivery.

  - The major advantage is that this option provides maximum flexibility in start dates for on campus instruction.

  - Potential disadvantages include loss of enrollment and more “gap year” choices by if we implement an online version.

Version 2): Fall semester starts on campus and pivots to online:

- This is the mirror of above, with same assumptions, advantages and challenges.

In all scenarios imaginable, there is an element of online instruction. The same investments outlined in Scenarios 1 (F2F, above) and 3 (fully online, below) are relevant.

Scenario 3:  Completely Online

With all undergraduate courses online, based on experience of both faculty and students, Spring Semester 2020, certain assumptions and investments must be considered.

Assumptions:

- Faculty will have engaged in professional development opportunities and created course modules for online delivery modality. Course lectures will be largely synchronous to encourage engagement, with asynchronous capture for time zone and contextual differences.

- The reason for fully remote with online teaching would be to prevent infection.

- If cases rise and large numbers of people start becoming sick and unable to work we could accommodate a percentage of loss of the teaching workforce.

- Each department should be asked to create a potential back-up instructor for each course. A greater percentage reduction in teaching workforce could result in course cancellation part way through the semester.

- CSU must abide by any state and county mandates or restrictions regarding the size of public gatherings, social distancing, and other health measures.

Institutional Investments (similar for models 1, 2, or 3)

- To support active measures to address and promote improved experience, draw on spring 2020 evidence (student surveys, course evaluations, academic unit reports) to identify issues, concerns, and best practices for fall implementation.

- In consultation with Deans/Dept Heads, faculty develop courses in an online form over the summer.  Professional development opportunities are available.  (Budget implication: Faculty ask for compensation. OGC advises that we cannot mandate faculty to work when they are not being paid. Provide modest [dean scholarships] to support professional development toward course development and pedagogical skills.)

- Invest in messaging and PR to highlight advanced preparation of instructors toward a quality remote/online experience. Each scenario includes online components and students must believe they will encounter excellent learning experiences both on campus and virtually. (Budget implication: personnel time and marketing costs)

- Invest in “virtual community” creation strategies including chat rooms, synchronous student peer, advisor and faculty meetings and link to co-curricular experiences involving student life, mentoring programs, teams, etc.

- Internship coordinators should create communication strategies for internship sites outlining potential contingencies, review contacts, and develop alternate approaches for student completing requirements.

Addenda

Summer Session Planning

In general, the outlook for summer session courses is positive:

- CSU summer courses are online, and CSU faculty have developed new courses (some specifically addressing the pandemic) and added additional sections of existing courses and CSU Summer office has facilitated relevant marketing and communication efforts.

- The Office of Financial Aid has devised new and attractive aid packages.

- Internships and field experiences are utilizing remote learning experiences or approved venues and protocols.

- While headcounts are down, total credit hours are higher than at this time last year. CSU Summer 2020 should generate more student learning and revenue than summer 2019.

- We recommend a proactive student Pulse survey before classes start or soon thereafter to identify areas where the campus can assist students.

Challenges for some summer programs:

- Many summer programs have been cancelled while others are still awaiting relevant health and safety protocols. Those do not have an online alternative available.

- The largest revenue and enrollment program is Youth Sports Camps, but others include the Early Childhood Center, Cooking Camps, and music and theater programs.

Recommendations:

- Prioritize safety protocols and guidance, immediately set a date for the earliest possible cancellation decision. recommended

  - Regard Pandemic Planning Committee optimism for a later start but set a decision date, e.g. camps are paused through July 1. By June 15 a firm decision will be rendered. Provides some revenue potential and support to families and gives clients information by which to plan.

- Cancelling for the whole summer is not recommended

  - If PPC indicates that summer recommendations are unpredictable, we could recommend cancelling these camps now.  We would have to accept revenue loss, but this would allow clients to make alternative plans.

  - If campus opens later in the summer and camps have been cancelled, there is potential for client dissatisfaction.

- Continue to wait on announcing some level of decision is not recommended

  - Clients call daily and lack of information to share creates increasing frustration.

  - Contracts and enrollments will need to be cancelled and refunded, and a date for doing so needs to be established now. The Youth Sports Camp session set for May 26 (families enrolled and paid in January), and venders contacts are still in place.

Data Collected for this report

- Square footage of all GA classrooms

- Estimate of capacity of each GA room assuming 6’ distancing

- Uniform time code

- Departmental prioritizations of F2F, hybrid, only remote

- Departmental analysis of feasibility of 8-week sessions

- Projected Professional Development Structure

- Professional Development support offerings for summer

Costs to Implement

- Teaching capacity will need to be increased due to additional breakouts in most courses

- Lecture capture in all GA classrooms

- Security (people, lighting, safe-walk)

- COVID testing of faculty and students

- Cleaning supplies

- Potential costs for rent for community spaces (Drake Center, Lincoln Center)